## Impact Analysis
ITG-TMP-620 |  | Document Version: | 4.1
Product ID: |  | NWM_P013 | Product Name: | ScreenXchange
Change Request (CR)/ Ticket Reference No: |  | BTS-10307 | Raised By: | Sangram Nikam
Change Request (CR)/ Ticket Status: |  | Resolved | Complexity (For CR): | 3 - Medium
Nature of Change: |  | New feature | Priority (For Ticket): | 3 – Critical
Prepared By: |  | Thirumavalavan P | Prepared Date: | 20-4-2024
S. No | Screen/ API method name Affected | Direct/Indirect Impact | Database Table Impact if any | Allocated To | Estimated Effort (in HRs) | Actual Start Date Time | Actual End Date Time | Actual Effort | Remarks
1 | Vendor, Agent module | Indirect | No | Thirumavalavan P | 42 | 20-4-2024 | 30-4-2024 | 42 | add the reminder mail log in the client screen
Total Actual Effort to complete the Change request/ Defect:
Assessed By: |  | Selva Kumar | Assessed Date: | 30-4-2024
Remarks |  | Reviewed